## Sheet1
Program | Project | M300 pillar Alignment | Completion date | Projected Status | Current project status | Comment Issues/ Main Risk/ Bottlenecks | Suggestion | Program type | Funding sources/ Funding Size/ Funding Structure[1] | Funding Status
Presidential Power Initiative (PPI) | Installation of 63MVA Mobile Substation at OKIGWE (50.4MW) | Pillar I: Expand power generation, transmission, and distribution grid infrastructure at competitive costs | 2026 | On track | Ongoing | Completion of dependency TCN lines project to evacuate power from new MSS | Coordinated Stakeholder engagement by Project Sponsor (TCN) to resolve ROW issues | Transmission Substations | FGNPC Capital/ | Secured
N1,801,666,020
| Conversion and expansion of New Abeokuta 132/33kV to 330KV with 2x 300MVA 330/132kV transformer and 4x 300kV line at New ABEOKUTA (480 MW) |  | 2026 | On track[2] | Ongoing | Financing Risk |  | Transmission Substations | Financing/ | Awaiting FEC
73948989
| Replacement of 1x90MVA with 1x 300MVA,330/132kV Transformer at ONITSHA (240 MW) |  | 2026 | On track | Ongoing |  |  | Transmission Substations | Financing/ | Awaiting FEC
17670459
| Replacement of burnt 1x150MVA 330/132kV and construction of 132kV line bay at AYEDE TS (120 MW) |  | 2027 | On track | Ongoing |  |  | Transmission Substations | Financing/ | Awaiting FEC
19134885
| Expansion of 132/33kV Offa substation with 4x132kV line bays and 1x 60MVA at OFFA TS (48 MW) |  | 2027 | On track | Ongoing |  |  | Transmission Substations | Financing/ | Awaiting FEC
28010358
| Reinforcement and replacement with 2X 60MVA 132/33KV at SOKOTO TS (96 MW) |  | 2027 | On track | Ongoing |  |  | Transmission Substations | Financing/ | Awaiting FEC
21146272
| Installation of 63MVA Mobile Substation at Ila Orangun (50.4 MW) |  |  |  | Awaiting FEC |  |  | Transmission Substations | FGNPC Capital/ | Secured
N2,795,426,336 and $5,291,797
| EPC of 2x 300MVA 330/132/33kV transformer, associated gear at OMOTOSHO & EPE (976 MW) |  |  |  | Awaiting FEC |  |  | Transmission Substations | Appropriation/ N56,918,697,358 and $92,367,176 | Fund release outstanding
| Construction and upgrade of 16no. transmission lines in locations across the country (Cumulative throughput 7,140 MW) |  | 2027 - 2028 | On track[3] |  | Financing Risk |  | Transmission Lines | Financing/ | Financing negotiations ongoing
$328,783,756.64
| Design, Supply, Installation, Testing and Commissioning of 2X60MVA 132/33kV Power Transformer and associated AIS Switchgear to Upgrade of 2X15MVA 132/33kV Transformer at Savanah (96 MW) |  | 2030 |  | YTC[4] |  |  | Transmission Substations | Financing/
38871390
| 2X 60 MVA 132/33kV Transformers, 2x 132kV Lines with 6x 33kV Outgoing feeder bays at OTUN EKITI (96 MW) |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
42043691
| 2X 60 MVA 132/33kV Transformers and Construction of 4x 132kV Lines with 8x 33kV Outgoing feeder bays at New Industrial Area, Kaduna State (96 MW) |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
43619798
| 2X 60 MVA 132/33kV Transformers and Construction of 4x 132kV Lines with 8x 33kV Outgoing feeder bays at EJULE, Kogi state (96 MW) |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
42344332
| 2x 300 MVA 330/132, 2x 100MVA 132/33kV Transformers, Construction of 4x 330kV line bays and 4x 132kV Line bays with 8x 33kV feeders at Lagos free trade Zone (LFTZ) (640 MW) |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
93149920
| 2x 300 MVA 330/132/33kV and 2x 100MVA 132/33kV Transformers, construction of 6x 330kV Lines and 4x 132kV Lines with 8x 33kV feeders at New Ijora (400 MW) |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
89660880
| 2X 60 MVA 132/33kV Transformers with 8x 33kV Outgoing feeder bays at SHAPATI, Ibeju lekki (96 MW) |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
42802600
| Construction of 2x 330kV Line Bays at AKANGBA TS to close the 330kV LOOP |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
20353464
| Construction of 2x 330kV Line Bays at ALAGBON TS to close the 330kV LOOP |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
37358185
| 2x 150 MVA 330/132kV and 2x 100MVA Transformers Construction of 4x 132kV Lines and 8x 33kV outgoing feeders (Ibadan-Ife Express way) ASEJIRE (240 MW) |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
83517270
| Construction and Installation of 2x 330kV Line bays, 4x 132kV Line bays, 2x 150MVA 330/132/33kV, 2x 60MVA 132/33kV Transformers and 8x 33kV Outgoing Feeder Bays at OKPOSI (Umuoghara) (240 MW) |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
78606418
| Construction and Installation of 4x 330kV Line bays and 2x 300MVA 330/132/33kV Interbus- Transformer at AFAM 2 (480 MW) |  | 2030 |  | YTC |  |  | Transmission Substations | Financing/
53297052
[1] The financing arrangements for the PPI are such that the Federal Government will provide 15% funding for all project costs under the PPI. The balance of 85% will be sourced from various financers and DFIs providing Export Credit Agency (ECA) backed financing.
[2] Project is on track even when financing arrangements are not in place due to Letter of Credit mechanism deployed as stop gap.
[3] FGNPC secured EPC commitment to prioritize the Ajah – Shapati line for delivery in 2027 using the 15% counterpart funds paid on the entire contract. All other lines will be progressed to survey stage pending securing financing arrangements.
[4] Yet to commence. Awaiting contract execution.