## KPI Requirements
Mission 300 REA KPI Requirements and Baseline Data
Tier | Pillar / Scope | KPI / Data Area | Metric / Data Field | Value | Unit | Year | Frequency | Scope / Breakdown | Source Programme(s)
Tier 1 | Pillar 2: Last-Mile Access | Mini-grids | Operational mini-grids | 554 | Number | 2026-08-01 | Quarterly | National aggregate | DARES / NEP / REF / TSD
Tier 1 | Pillar 2: Last-Mile Access | Mini-grids | Operational mini-grid installed capacity | 138.8 | MW | 2026-08-01 | Quarterly | National aggregate | DARES / NEP / REF / TSD
Tier 1 | Pillar 2: Last-Mile Access | Mini-grid access | Active household mini-grid connections | 446750 | Number | 2026-08-01 | Quarterly | National aggregate | DARES / NEP / REF / TSD
Tier 1 | Pillar 2: Last-Mile Access | Mini-grid access | Active MSME mini-grid connections | 26525 | Number | 2026-08-01 | Quarterly | National aggregate | DARES / NEP / REF / TSD
Tier 1 | Pillar 2: Last-Mile Access | Solar Home Systems | Cumulative SHS units deployed | 1476608 | Number | 2026-08-01 | Quarterly / Annual | National aggregate | DARES / NEP / REF / TSD
Tier 1 | Pillar 4: Private-Sector Participation | Private-sector pipeline | Mini-grid developers with signed grant agreements | 426 | Number | 2026-08-01 | Annual / Quarterly | Programme / developer | DARES / REF
Tier 1 | Pillar 4: Private-Sector Participation | Private-sector pipeline | Planned sites or connections under signed agreements | 41066 | Number | 2026-08-01 | Quarterly | Programme / developer | DARES
Tier 1 | Pillar 4: Private-Sector Participation | Private capital | Private capital committed since January 2025 | 750000000 | Currency not stated | 2026-08-01 | Quarterly / Bi-annual | Project / instrument | DARES
Tier 1 | Pillar 4: Private-Sector Participation | Private capital | Private capital deployed or disbursed since January 2025 | 27747329.3 | Currency not stated | 2026-08-01 | Quarterly / Bi-annual | Project / instrument | DARES
Tier 1 | Cross-Cutting | Programme financing | Total approved programme financing | 750000000 | Currency not stated | 2026-08-01 | Quarterly / Bi-annual | Programme / funder | DARES
Tier 1 | Cross-Cutting | Programme financing | Grant amount | 293576600 | Currency not stated | 2026-08-01 | Quarterly / Bi-annual | Programme / funder | DARES
Tier 1 | Cross-Cutting | Programme financing | Loan amount | 750000000 | Currency not stated | 2026-08-01 | Quarterly / Bi-annual | Programme / funder | DARES
Tier 1 | Cross-Cutting | Programme financing | Private co-financing | 750000000 | Currency not stated | 2026-08-01 | Quarterly / Bi-annual | Programme / instrument | DARES
Tier 1 | Cross-Cutting | Programme financing | Amount committed | 750000000 | Currency not stated | 2026-08-01 | Quarterly / Bi-annual | Programme / funder | DARES
Tier 1 | Cross-Cutting | Programme financing | Amount disbursed and expenditure to date | 27747329.3 | Currency not stated | 2026-08-01 | Quarterly / Bi-annual | Programme / funder | DARES
Tier 2 | Pillar 2: Last-Mile Access | Mini-grid pipeline | Planned mini-grid connections | 26525 | Number | 2026-08-01 | Quarterly | National / programme / developer / project stage | DARES
Tier 2 | Pillar 2: Last-Mile Access | Mini-grid pipeline | Mini-grid pipeline sites | 426 | Number | 2026-08-01 | Quarterly | Programme / developer / project stage | DARES / NEP / REF / TSD
Tier 2 | Pillar 2: Last-Mile Access | Productive use | MSMEs connected through DRE | 29275 | Number | 2026-08-01 | Semi-annual | Programme / technology / enterprise type | NEP / REF / TSD
Tier 2 | Pillar 2: Last-Mile Access | Productive use | Productive-use equipment deployed | 950 | Number | 2026-08-01 | Annual | Programme / equipment type | NEP / TSD
Tier 2 | Pillar 2: Last-Mile Access | Gender and inclusion | Women-led or women-owned MSMEs receiving DRE connections | 11035 | Number | 2026-08-01 | Semi-annual | Programme / technology / enterprise sector | NEP
Tier 2 | Pillar 2: Last-Mile Access | SHS procurement | SHS units procured through approved DRE framework | 709513 | Number | 2026-08-01 | Quarterly | Programme / procurement / contract | DARES / NEP / REF / TSD
Tier 2 | Pillar 2: Last-Mile Access | SHS procurement | Award or agreement date and implementation status | 05/02/2025 / Deployed | Date / status | 2026-08-01 | Quarterly | Programme / contract | DARES / NEP / REF / TSD
Tier 2 | Pillar 4: Private-Sector Participation | Project Preparation Facility | Facility operational status | Yes | Yes/No | 2026-08-01 | Quarterly | Facility | Not stated

## Project Register
Mission 300 Ongoing Project Register - Rural Electrification Agency (REA)
Program | Project | M300 Pillar Alignment | Projected Completion Date | Projected Status | Current Project Status | Comment - Issues/Main Risk/Bottlenecks | Suggestion | Program Type | Funding Sources/Funding Size/Funding Structure | Funding Status
Energizing Education Programme (EEP) Phase III | Modibbo Adama University 5MW Solar Hybrid Power Project | Pillar 2: Last-Mile Access | August/September 2025 | Completed / Commissioned | Completed | N/A | N/A | Donor Loan Funded | African Development Bank (AfDB) financing under the Nigeria Electrification Project (NEP) | Disbursement in Tranches Ongoing
| Federal University Dutsin-Ma 1.9MW Solar Hybrid Power Project | Pillar 2: Last-Mile Access | August/September 2025 | Completed | Completed | N/A | N/A | Donor Loan Funded |  | Disbursement in Tranches Ongoing
| Federal University of Lafia 1.6MW Solar Hybrid Power Project | Pillar 2: Last-Mile Access | August/September 2025 | Completed | Completed | N/A | N/A | Donor Loan Funded |  | Disbursement in Tranches Ongoing
| Federal University Lokoja 1.7MW Solar Hybrid Power Project | Pillar 2: Last-Mile Access | August/September 2025 | Completed | Completed | N/A | N/A | Donor Loan Funded |  | Disbursement in Tranches Ongoing
| Federal University of Technology Owerri 8.2MW Solar Hybrid Power Project | Pillar 2: Last-Mile Access | August/September 2025 | Completed | Completed | N/A | N/A | Donor Loan Funded |  | Disbursement in Tranches Ongoing
| University of Port Harcourt and Teaching Hospital 10.7MW Solar Hybrid Power Project | Pillar 2: Last-Mile Access | August/September 2025 | Completed | Completed | N/A | N/A | Donor Loan Funded |  | Disbursement in Tranches Ongoing
| University of Uyo 2.9MW Solar Hybrid Power Project | Pillar 2: Last-Mile Access | August/September 2025 | Completed | Completed | N/A | N/A | Donor Loan Funded |  | Disbursement in Tranches Ongoing
| Federal University of Technology Akure 4.5MW Solar Hybrid Power Project | Pillar 2: Last-Mile Access | August/September 2025 | Completed | Completed | N/A | N/A | Donor Loan Funded |  | Disbursement in Tranches Ongoing